## README
TJF Operations Toolkit
Four linked trackers for running the Foundation day to day ¦ v1.0, 26 September 2026
What's in this workbook
Sheet | What it tracks | Pre-filled with
1. Task & Decision Tracker | Every open item flagged across the five program dossiers, the district decision, registration and pillar leads, in one place with owners and status. | 45 real items pulled from the Health, Environment, Livelihoods, Education and Animal Health Initiative dossiers
2. Recruitment Tracker | Candidates against the roles TJF is actively seeking: board, advisors, partners, and the four pillar leads. | The roles from README's "Seeking at This Stage" plus the four pillar-lead and two AHI partner roles
3. Donor & Partner CRM | Outreach status for every funder identified so far, with terms, fit notes and next actions. | 18 funders from the grants calendar and the dedicated funder review
4. M&E Dashboard | One rolled-up view of the outcome-level indicators from all five program logframes. | 25 outcome indicators across Health, Environment, Livelihoods, Education and the Animal Health Initiative
How the four sheets connect
• A role filled in the Recruitment Tracker (e.g. a pillar lead) should be copied into that item's Owner column in the Task Tracker.
• A funder that moves to "Applied" or "Awarded" in the Donor CRM should update the matching item's status in the Task Tracker (e.g. "Cost the budget structure" or "Secure multi-year funding").
• The M&E Dashboard only fills in once a program is far enough along to have baseline data — for now, every row should read "Not started" honestly.
• This workbook is internal. Keep it out of the public repository, same as the dossiers it draws from.
Colour legend
Yellow fill, blue text | Fill in yourself
Black text | Pre-filled from the dossiers — update as things change

## 1. Task Tracker
Task & decision tracker
Every open item flagged across the five dossiers, plus cross-cutting decisions. Update Status and Owner as things move.
Program / Area | Item | Status | Priority | Owner | Notes | Last updated
Cross-cutting | Name the four pillar leads (Health, Education, Livelihoods, Environment) | Open | High |  | Role profiles drafted; no candidates identified yet.
Cross-cutting | Choose shared operating district(s) for the year | Resolved | — | Leadership | Decided 25 Sep 2026: Adjumani, Moyo, Nebbi and Omoro (all four, not narrowed to one). | 2026-09-25
Cross-cutting | Complete legal registration (Company Ltd by Guarantee + NGO status) | In progress | High |  | In its final stages as of 25 Sep 2026. | 2026-09-25
Cross-cutting | Amend constitution's objects clause to cover animal health / One Health work | In progress | High |  | In its final stages as of 25 Sep 2026. | 2026-09-25
Cross-cutting | Decide Year-1 pilot goal: Option A (as published) vs Option B (evidence-aligned) | Resolved | — | Claude / leadership | Option B adopted for all four pillars, 21 Sep 2026. | 2026-09-21
Cross-cutting | Recolour AHI paw mark into TJF palette; export real logo files | Resolved | — | Claude | Delivered 25 Sep 2026: icon, horizontal/stacked/reversed lockups, avatar (SVG+PNG). | 2026-09-25
Cross-cutting | Mini brand guide for the AHI mark | Resolved | — | Claude | 2-page PDF delivered 25 Sep 2026. | 2026-09-25
Health | District Health Office conversation on scope, incentives and CAHW-equivalent supervision | Open | High |  | Needed before Gate 1 (month 4 of the pilot).
Health | Confirm timing of the next national net campaign in the chosen district | Open | Medium |  | Determines whether campaign-support activity is possible in year 1.
Health | Cost the budget structure with local quotations | Open | High |  | Needed before any funding request.
Health | Choose a technical community-health partner and an academic evaluation partner | Open | High
Health | Verify: West Nile / chosen-district malaria transmission level | Open | Low |  | Regional data only so far; district-specific data needed.
Health | Verify: reported malaria-funding phase-out claim before any public use | Open | Low |  | Single news source; do not publish unverified.
Environment | Identify the two partner schools and confirm available land | Open | High |  | Sets the tree-planting number.
Environment | Ask the District Water Office for its list of non-functional boreholes | Open | High
Environment | Check the local planting season / rains timing | Open | Medium |  | Determines the delivery-phase schedule.
Environment | Cost the budget structure with nursery, mechanic and lab quotations | Open | High
Environment | Ask GEF Small Grants Programme whether in-kind support counts toward co-financing | Open | Medium |  | Affects whether GEF SGP is a viable route.
Environment | Verify: forest-loss and tree-cover-loss figures before publishing | Open | Low |  | Press-sourced only so far.
Livelihoods | Choose a savings-group (VSLA) training partner | Open | High
Livelihoods | Confirm Uganda Microfinance Regulatory Authority and district requirements for the groups | Open | High
Livelihoods | Map other savings/enterprise programmes already active in the chosen district | Open | Medium |  | Avoid duplication.
Livelihoods | Cost the budget structure | Open | High
Livelihoods | Agree grant-selection criteria and committee membership | Open | Medium
Livelihoods | Verify: typical VSLA group size and cycle length with the chosen partner | Open | Low
Education | Choose the district and specific partner school | Open | High |  | District pool decided; specific school still open.
Education | Cost a full-cycle sponsorship per student | Open | High |  | Sets the cohort size — do not enrol beyond what is funded.
Education | Secure multi-year funding for the sponsorship cohort | Open | High |  | Gate 1 condition.
Education | Check school power, room and security for the digital hub | Open | High |  | Prevents idle equipment.
Education | Confirm the school calendar and term dates | Open | Medium |  | Sets enrolment timing.
Education | Verify: obligations under the Data Protection and Privacy Act 2019 for children's data | Open | Medium
Animal Health Initiative | Commission district dog-population estimates (all four districts) | Open | High |  | Needed to fix vaccination targets.
Animal Health Initiative | Cost the full budget with local quotations (currently a high-level placeholder) | Open | High
Animal Health Initiative | Confirm the Foundation's own contribution to the funding mix (working assumption: 15%) | Open | High |  | Needs written confirmation from leadership.
Animal Health Initiative | Identify and sign a clinical / veterinary partner | Open | High |  | Clinical leadership is by partnership, not direct hire.
Animal Health Initiative | Develop the CAHW income model in full detail (fee levels, subsidies, kit costs) | Open | High
Animal Health Initiative | Decide district sequencing / start order across the four confirmed districts | Open | Medium |  | Districts confirmed; order not yet decided.
Animal Health Initiative | Set a firm programme start date | Open | Medium |  | Depends on funding and registration completion.
Animal Health Initiative | Commission local-language versions of the slogan | Open | Low |  | Do not assume Swahili; ask local staff.
Animal Health Initiative | Tailor the grant concept note per funder as calls are identified | Open | Medium
Animal Health Initiative | Resolve items marked "to verify" in the fact-check register before external release | Open | Medium |  | PASERA dates, SARE stage year, NRES 70%/1.5M dog target, others.
Funding / Partnerships | Approach GARC, vaccine-industry donors and Mission Rabies as early partners | Open | High |  | Best-fit funders for AHI at this stage.
Funding / Partnerships | Watch for the next WHO African Region / TDR Impact Grants round | Open | Medium |  | Last round's deadline (15 Sep 2026) has passed.
Funding / Partnerships | Seek a warm referral into Segal Family Foundation | Open | Medium |  | Does not accept unsolicited proposals.
Summary
Status | Count
Open | 38
In progress | 2
Resolved | 4
Blocked | 0

## 2. Recruitment Tracker
Volunteer & board recruitment tracker
Roles TJF is actively seeking, from the README's "Seeking at This Stage" plus the four pillar leads and two AHI partner roles.
Category | Role | What they'd do | Status | Candidate(s) | Contact | Next step | Date added
Governance | Founding Board Member | Sit on TJF's founding board; governance, oversight, fundraising networks. | Open |  |  | Identify and approach candidates
Governance | Incorporation & Legal Support | Guide the Company Ltd by Guarantee / NGO registration through to completion. | In progress |  |  | Registration in final stages — confirm who is currently advising
Governance | Strategic & Institutional Partner | Organisational partnership at the institutional level (not a funder relationship specifically). | Open
Governance | Technical & Program Advisor | Advisory input across the four pillars; not a full board seat. | Open
Governance | Early Corporate & Philanthropic Partner | First corporate or philanthropic relationships ahead of a full fundraising push. | Open
Pillar Lead | Health & Wellbeing Lead | Owns the Community Health Champions pilot: district relations, budget sign-off, accountable for targets. | Open |  |  | Role profile drafted — post / circulate
Pillar Lead | Education & Youth Development Lead | Owns the Jopetnah Scholars + Future-Ready Lab pilot. | Open |  |  | Role profile drafted — post / circulate
Pillar Lead | Poverty Alleviation & Livelihoods Lead | Owns the Cooperative Savings Circles pilot. | Open |  |  | Role profile drafted — post / circulate
Pillar Lead | Environment & Community Development Lead | Owns the Green Neighborhoods + Water & Sanitation pilot. | Open |  |  | Role profile drafted — post / circulate
AHI Partnership | Clinical / Veterinary Partner | Clinical leadership for the Animal Health Initiative — protocols, CAHW training, licensed oversight. By partnership, not direct hire. | Open |  |  | High priority — hardest gap to fill per the blueprint
AHI Partnership | Academic Partner (veterinary or public health faculty) | Baseline study design and independent evaluation. | Open
Program Partnership | Savings-Group (VSLA) Training Partner | Delivers the Livelihoods pillar's group formation and training methodology. | Open
Program Partnership | Community Health Technical Partner | Training design and supervision for Community Health Champions. | Open
Summary
Status | Count
Open | 12
Sourcing | 0
Interviewing | 0
Offered | 0
Filled | 0
On hold | 0

## 3. Donor CRM
Donor & partner CRM
Every funder identified so far (grants calendar + the dedicated funder review), with terms and fit notes as last checked.
Funder | Programme fit | Type | Amount range | Deadline / cadence | Outreach status | Fit note | Contact person | Last contact | Next action
Global Alliance for Rabies Control (GARC) | Animal Health Initiative | Network + small grants | Varies (small grants) | Rolling; World Rabies Day is a natural entry point | Not started | Best first move — built for local NGOs; free vaccination-tracking tools; Rabies Center of Excellence status builds credibility. |  |  | Introduce TJF and the initiative
Mission Rabies / Worldwide Veterinary Service | Animal Health Initiative | Technical / clinical partner | In-kind (clinical support) | Rolling | Not started | Already active in Uganda — natural candidate for the still-open clinical/veterinary partner role. |  |  | Approach as a partner, not a funder
MSD Animal Health (Afya programme) | Animal Health Initiative | In-kind vaccine donation | Doses, not cash | Rolling, via partner NGOs | Not started | Would cut the largest AHI cost line. Needs registration + a named clinical partner first. |  |  | Hold until registration completes
Boehringer Ingelheim (STOP Rabies, via GARC) | Animal Health Initiative | In-kind vaccine donation | Doses, not cash | Rolling, via GARC | Not started | Same as above — approach through GARC once that relationship exists. |  |  | Hold until GARC contact made
Rabies Free Africa | Animal Health Initiative | Programme grant | Varies | Check current call | Not started | Funds mass dog vaccination specifically in East Africa. |  |  | Research current call status
WHO African Region / TDR Impact Grants | Animal Health Initiative | Small research grant | Up to $15,000 (12 months) | Last round closed 15 Sep 2026 | Not started | NGOs eligible; One Health and zoonotic disease are priority areas. Watch for the next round. |  |  | Watch for next call
Pandemic Fund (via FAO/WHO/UNICEF implementing entities) | Animal Health Initiative | Subpartnership | Varies | Through implementing entities | Not started | Government-facing — approach as a community-delivery subpartner, not a direct applicant. |  |  | Identify the Uganda implementing entity
US Government global health opportunities (State Dept / CDC Uganda) | Animal Health Initiative / Health | Institutional grant / subaward | Varies; State calls can start at $500,000 | Check grants.gov / SAM.gov continuously | Not started | USAID was dissolved in 2025; routes now run through the State Department. Best pursued as a subaward via an established prime. |  |  | Monitor grants.gov
Gates Foundation | Cross-cutting | Major grant | Large | By invitation only | Not started | Does not accept cold proposals. Revisit after pilot results, likely via a consortium. |  |  | Revisit post-pilot
Wellcome | Animal Health Initiative (research angle) | Research grant | £1–8 million (clinical trial awards) | Check current calls | Not started | Funds research, not delivery. TJF would be a community-delivery partner under an academic-led bid, not the lead applicant. |  |  | Identify a research-lead partner (e.g. Makerere)
Segal Family Foundation | Livelihoods / cross-cutting | Grant | First-time grants typically $10,000–40,000 | Rolling, referral-based | Not started | Does not accept unsolicited proposals — needs a warm referral. |  |  | Seek a referral
MTN Uganda Foundation — Changemakers | Education / cross-cutting | Grant | Share of ~$130,000 across ~25 grassroots projects | Phased calls | Not started | Realistic entry point for a first small grant; requires co-branding. |  |  | Watch for next call window
Stanbic Bank Uganda — CSR | Livelihoods / Education | Grant / sponsorship | Varies | Annual announcements | Not started | Fits savings groups and financial literacy specifically. |  |  | Watch for annual announcement
Airtel Foundation — CSR | Education | Grant / in-kind | Varies | Rolling proposals | Not started | Fits the digital literacy hub partnership. |  |  | Draft a hub-specific proposal
Mastercard Foundation Scholars (Makerere) | Education | Scholarship placement (not a grant to TJF) | N/A | 2026/27 cycle closed 5 Jun 2026 | Not started | Progression route for TJF-sponsored students, not a funding source for TJF itself. |  |  | Note as a referral pathway
GEF Small Grants Programme (UNDP Uganda) | Environment / Livelihoods | Grant | Up to $40,000–50,000 | Rolling calls; last closed 2 Jul 2026 | Not started | Needs a registration certificate and ~50% co-financing. Strong fit once registered. |  |  | Ask whether in-kind counts as co-financing
CEMA Climate Justice Small Grants | Environment | Small grant | $1,000–5,000 | Deadline 31 Dec 2026 | Not started | Small enough to start the school tree-planting component before full registration completes. Confirm eligibility directly. |  |  | Confirm current eligibility
UNEP Mountains ADAPT Small Grants | Environment | Small grant | Up to $30,000 | Deadline was 15 Sep 2026 (passed) | Not started | Only fits if the chosen district is a mountain landscape. Watch for the next round. |  |  | Confirm district fit; watch for next round
Summary
Status | Count
Not started | 18
Researching | 0
Contacted | 0
In discussion | 0
Applied | 0
Awarded | 0
Declined | 0

## 4. M&E Dashboard
Program M&E dashboard
The lead outcome indicator for each of the five programs' logframes, rolled up into one view. Full indicator sets live in each dossier's own Results Framework / Indicator Tracker.
Program | Outcome | Lead indicator | Baseline | Target | Actual | As of | RAG status | Notes
Animal Health Initiative | O1 — Vaccination coverage | % of owned dogs vaccinated against rabies | Baseline pending | ≥65% per district at M24 (aiming 70%) |  |  | Not started | Pilot not yet funded or started.
Animal Health Initiative | O2 — Bite care access | % of reported bite cases completing full PEP course | Baseline pending | ≥80% at M24 |  |  | Not started
Animal Health Initiative | O3 — CAHW network | CAHWs trained, equipped and still active after 12 months | 0 | 30–45 at M24 |  |  | Not started
Animal Health Initiative | O4 — Community knowledge | % of school children with correct bite first-aid knowledge | Baseline pending | ≥70% at M24 |  |  | Not started
Animal Health Initiative | O5 — Evidence uptake | Districts integrating the CAHW / One Health model into their plans | 0 | ≥1 district by M36 (proposed) |  |  | Not started
Health (Community Health Champions) | O1 — Net use | % of pregnant women / children under 5 who slept under a net | Baseline pending | Rise toward national 85% goal |  |  | Not started | District and school not yet finalised.
Health (Community Health Champions) | O2 — Care-seeking | % of children under 5 with fever tested/treated within 24h | Baseline pending | Increase against baseline |  |  | Not started
Health (Community Health Champions) | O3 — Vaccine completion | % of children with dose 1 who receive dose 4 (Champion-supported area) | Facility registers pending | Increase against baseline |  |  | Not started
Health (Community Health Champions) | O4 — Antenatal attendance | % of pregnant women attending 4+ antenatal visits | Facility registers pending | Increase against baseline |  |  | Not started
Health (Community Health Champions) | O5 — Champion retention | % of trained Champions still active after 12 months | N/A | Proposed ≥75%; confirm with district |  |  | Not started
Environment (Green Neighborhoods + WASH) | O1 — Tree survival | % of tagged trees alive at 12 months | N/A | Proposed ≥80% |  |  | Not started | Partner schools and borehole not yet identified.
Environment (Green Neighborhoods + WASH) | O2 — School ownership | Environment clubs meeting at least monthly at 12 months | 0 | 2 of 2 schools |  |  | Not started
Environment (Green Neighborhoods + WASH) | O3 — Water reliability | Borehole functional, <30 days downtime/year | Non-functional | Met at 6 and 12 months |  |  | Not started
Environment (Green Neighborhoods + WASH) | O4 — Community management | Water user committee meets quarterly, holds a repair fund | None | Met at 12 months |  |  | Not started
Environment (Green Neighborhoods + WASH) | O5 — Hygiene practice | % of pupils/households with a handwashing point (water + soap) | Baseline pending | Increase against baseline |  |  | Not started
Livelihoods (Cooperative Savings Circles) | O1 — Groups functioning | Groups meeting weekly with up-to-date records at 6 and 12 months | 0 | Proposed 4 of 5 groups |  |  | Not started | Training partner not yet chosen.
Livelihoods (Cooperative Savings Circles) | O2 — Saving & borrowing | % of members with savings; median savings at share-out | 0 | Set after 3 months of data |  |  | Not started
Livelihoods (Cooperative Savings Circles) | O3 — Reaches the poorer | % of members from poorer households (scorecard) | Baseline pending | Proposed ≥50% |  |  | Not started
Livelihoods (Cooperative Savings Circles) | O4 — Grant business survival | % of grantee businesses operating 6 months after the grant | N/A | Proposed ≥80% |  |  | Not started
Livelihoods (Cooperative Savings Circles) | O5 — Women's voice | % of women reporting a say in how savings/loans are used | Baseline pending | Increase against baseline |  |  | Not started
Education (Jopetnah Scholars + Future-Ready Lab) | O1 — Retention | % of sponsored students still enrolled at end of school year | All enrolled at start | Proposed ≥90% |  |  | Not started | Cohort size depends on securing full-cycle funding.
Education (Jopetnah Scholars + Future-Ready Lab) | O2 — Mentoring reach | % of sponsored students attending monthly mentoring | 0 | Proposed ≥80% |  |  | Not started
Education (Jopetnah Scholars + Future-Ready Lab) | O3 — Digital skills | % of hub students passing a practical ICT test | Test at start | Proposed ≥70% |  |  | Not started
Education (Jopetnah Scholars + Future-Ready Lab) | O4 — Hub sustainability | Hub open for scheduled sessions on planned days | N/A | Proposed ≥90% |  |  | Not started
Education (Jopetnah Scholars + Future-Ready Lab) | O5 — Girls' participation | Girls as a share of hub and sponsored-student cohorts | N/A | At least half |  |  | Not started
Rollup by program
Program | On track / Achieved | At risk | Off track | Not started
Animal Health Initiative | 0 | 0 | 0 | 5
Health (Community Health Champions) | 0 | 0 | 0 | 5
Environment (Green Neighborhoods + WASH) | 0 | 0 | 0 | 5
Livelihoods (Cooperative Savings Circles) | 0 | 0 | 0 | 5
Education (Jopetnah Scholars + Future-Ready Lab) | 0 | 0 | 0 | 5